## Sheet1
CSI4142 - Project 2023
Phase 3- OLAP and BI Dashboard
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
OLAP queries
Drill down, roll up | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Slice | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Dice | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Composite OLAP - 4 queries | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Icebergs | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Windowing - partition | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Window | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
BI dashboard
Design of data mart | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Importing data | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
OLAP queries | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Figures | Chentao Jin | 2024-04-04 | 2024-04-05 | 0.3 | 0.3
Other tasks - please specify